KAME

See It, Swipe It, Own It

Social Media Marketing Strategy V2.0

0 → 10K Waitlist  |  0 → 1M Social Traction

With 14-Day Launch Sprint & Automated Marketing Workflow

March 2026  |  Confidential  |  V2.0

# 1. Executive Summary

This document outlines Kame’s pre-launch social media marketing strategy to achieve 10,000 waitlist signups and 1M aggregate social impressions before app store launch. V2.0 adds a concrete 14-day launch sprint with daily to-dos and a fully automated marketing workflow using agentic AI tools.

Core Thesis: Kame’s AI virtual try-on produces inherently viral “before/after” content. The strategy combines a Robinhood-style referral waitlist, SKIMS-inspired 3-layer influence model, Gymshark-style community challenges, and Cluely-level founder-led content intensity — all powered by an automated n8n/Make.com pipeline.

Budget: $50–$100/month (tools only). No paid ads until post-waitlist.

Timeline: 14-day launch sprint, then ongoing 12-week campaign.

Team: 2 founders (Jo + Ryan). No marketing hire until 5K waitlist.

# 2. Strategic Framework: The Dual Flywheel

Two interconnected flywheels feed each other:

Flywheel 1 — Social Traction Engine: @kameapp (brand account) publishes polished UI mockups, AI try-on demos, and product teasers. Builds brand credibility as the “storefront.”

Flywheel 2 — Founder Story Engine: Jo and Ryan’s personal accounts share BTS content: building the app, leaving corporate, the emotional journey. Builds parasocial connection and drives traffic to the brand account and waitlist.

The Connection: Every founder reel links to @kameapp. Every brand post links to the waitlist. The waitlist has referral mechanics that create a third viral loop. All three loops compound.

## 2.1 The 2026 Instagram Algorithm Rules

Rule 1 — DM Shares > Everything: The #1 ranking signal is whether someone sends your Reel to a friend. Create content people want to forward.

Rule 2 — Users control their algorithm: Instagram’s “Your Algorithm” for Reels lets users personalize recommendations. Generic viral bait is dead. Niche consistency wins.

Rule 3 — Raw beats polished: Overly produced content is ignored as “noise.” The 2026 aesthetic is handheld, honest, founder-led.

Rule 4 — Trailer → Movie: Short Reels (15–30s) hook attention. Long-form Reels (up to 20 min) deliver depth. Use both.

Rule 5 — Community depth > follower width: Broadcast Channels and private groups create sustainable engagement that compounds.

# 3. Waitlist Strategy: The Referral Engine

## 3.1 Waitlist Platform & Design

Recommended Platform: GetWaitlist ($15/mo) — best balance of referral tracking, free tier for testing, and ease of setup. Alternative: KickoffLabs ($29/mo) for more gamification.

Landing Page (Single Page): Built on Framer or Carrd ($0–10/mo). Domain: joinkame.com or trykame.com.

- Hero: “See yourself in every outfit before you buy. Swipe to shop.”

- 3-second looping video/GIF of AI try-on transformation

- Single email field + “Get Early Access” CTA (coral gradient)

- Live social proof counter: “Join 2,847 fashion lovers already in line”

- Post-signup: Queue position + “Refer 3 friends to skip ahead” with share buttons

## 3.2 Referral Incentive Tiers

- 3 referrals → Priority beta access (first wave)

- 5 referrals → 1 month free Premium at launch

- 10 referrals → Founding Member badge (permanent) + early feature access

- 25 referrals → Personal style consultation with the Kame team

## 3.3 Website: Yes, But Minimal

A single-page waitlist landing page is essential as the universal link destination, SEO foundation, credibility signal for press/influencers, and analytics hub. Not a full website. Build in Framer or Carrd, embed the waitlist widget. Total: $0–10/month.

# 4. Instagram Strategy: Dual Account Playbook

## 4.1 @kameapp (Brand Account)

Purpose: Professional, aspirational, product-focused. Where investors, press, and users see a polished brand.

Pillar A — AI Try-On Demos (40%): Before/after transformations. Product photo → AI try-on. Format: Carousel or Reel with transition. Hook: “What SHEIN shows you vs. what it looks like on YOUR body.”

Pillar B — UI Showcase (25%): Screen recordings or animated mockups of the swipe interface, onboarding, favorites. Uses Kame brand system.

Pillar C — Fashion Education (20%): Carousels like “5 outfit combos under $50”, “How to dress for your body shape.” Builds audience beyond app-interested users.

Pillar D — Social Proof (15%): Waitlist milestones, beta reactions, press mentions, team milestones.

## 4.2 Founder Accounts — Building in Public

Series 1 — “MBB to Startup”: Day-in-the-life. 9–9 at BCG, then 9pm–3am building Kame. Text: “What my colleagues don’t know I’m building.”

Series 2 — “Vibe Coding a $1M App”: Screen recordings building features with Claude/Cursor. Real progress updates.

Series 3 — “The Numbers Don’t Lie”: Transparent updates: waitlist growth, API costs, investor conversations.

Series 4 — “Fashion Fails → AI Fixes”: Order online, show disappointment, show how Kame would have prevented it.

Cadence: 3–4 Reels/week, daily Stories (polls, BTS, Q&A). Cross-post to TikTok.

# 5. Influencer & KOL Strategy

## 5.1 The 3-Layer Influence Model (SKIMS Playbook)

Layer 1 — Founder (Jo + Ryan): Personal brands as the core distribution channel. Goal: 100K+ combined followers over 6 months.

Layer 2 — Micro-Creators (10–20 people): Fashion/style nano and micro-influencers who genuinely match Kame’s aesthetic. Long-term relationships, not one-offs.

Layer 3 — User-Generated Content: Every beta user who shares a try-on result becomes Layer 3. This is the compound growth engine.

## 5.2 Three-Phase Plan

Phase 1 (Weeks 1–4) Seed: 10–20 nano-influencers (1K–10K). Cost: Free (beta access). Goal: 500–1K signups + 10–20 UGC pieces.

Phase 2 (Weeks 5–8) Amplify: 5–10 micro-influencers (10K–50K). Cost: $100–300/post. Goal: 3K–5K additional signups.

Phase 3 (Post-Launch) Scale: 2–5 mid-tier (50K–500K). Budget: $500–2K/collab. Affiliate partnerships with trackable links.

# 6. KPIs & Measurement

| Metric | Week 4 | Week 8 | Week 12 |
| --- | --- | --- | --- |
| Waitlist Signups | 1,000 | 5,000 | 10,000 |
| IG Followers (Brand) | 500 | 2,500 | 8,000 |
| IG Followers (Founder) | 1,000 | 5,000 | 15,000 |
| Total Impressions | 50K | 300K | 1M+ |
| Referral Rate | 15% | 25% | 30% |
| Engagement Rate | 5%+ | 4%+ | 3.5%+ |

# 7. Case Studies: What’s Working NOW (2025–2026)

## 7.1 Cluely (2025) — Founder-Led Viral Machine

Result: $3M ARR in 3 months, $15M raise from a16z, $120M valuation.

Key Tactic — Content Army: 700+ “clippers” repost content across TikTok/IG Reels. Paid per view, not per clip. 1% drive majority of views.

Key Tactic — Team = Content: CMO has 190K LinkedIn followers. Every team member creates content. Office doubles as content studio.

Warning: Cluely later admitted to lying about revenue. Virality without product-market fit is unsustainable. Attention is fuel, not the engine.

Steal for Kame: Clipper model (budget version: 10–20 micro-creators reposting). Founder as protagonist. But build product quality first.

## 7.2 SKIMS (2019–2026) — 3-Layer Fashion Influence

Result: $4B valuation. 7M IG followers. 56,000 creator mentions by 2024.

Key Tactic — 3 Layers: Kim (founder) at top, strategic collaborators (Sabrina Carpenter, Neymar) in middle, real customer UGC at base. Each layer feeds the next.

Key Tactic — Cultural Timing: Campus Collection timed to RushTok trend. Real college students, not models. Olympics partnership. Every drop is an event.

Steal for Kame: 3-layer model is our blueprint. Time content pushes to fashion moments. Real users > polished models.

## 7.3 Gymshark (Ongoing) — Community Challenge Flywheel

Result: $1.6B valuation. 7.7M IG followers. #Gymshark66 = 65.7M engagements.

Key Tactic — Habit Challenge: #Gymshark66 (66 days to form a habit). Users share daily progress. Creates months of UGC and keeps audience engaged.

Steal for Kame: Create #KameTryOn or #KameSwipeChallenge. Users share AI try-on results. The format IS the challenge.

## 7.4 Olipop (2024–2025) — Organic Trend Amplification

Result: 570M media impressions. 50M TikTok views. $0 paid spend.

Key Tactic: Didn’t manufacture the trend. Users created “Sleepy Girl Mocktail” organically. Olipop amplified what was already happening.

Steal for Kame: Monitor #OnlineShoppingFails and fashion disappointment content. Insert Kame as the solution. Amplify, don’t manufacture.

# 8. 14-Day Launch Sprint: Day-by-Day Workplan

Goal: Set up all marketing infrastructure, publish first content, open waitlist, and establish automated workflows within 2 weeks. Each day has a primary owner (Jo or Ryan) and estimated hours.

## WEEK 1: Foundation & Infrastructure

### Day 1 (Monday) — Domain, Waitlist Platform & Brand Accounts

Owner: Jo (3h) + Ryan (2h)

| Task | Details | Done? |
| --- | --- | --- |
| Secure domain | Purchase joinkame.com (or trykame.com). Use Namecheap or Cloudflare Registrar (~$10/yr). | / |
| Sign up GetWaitlist | Create account ($15/mo). Configure referral tiers (3/5/10/25). Set up email confirmation. | ☐ |
| Create @kameapp IG | Business account. Upload Kame logo. Write bio: “AI-powered fashion try-on. See it on YOU before you buy. 👇 Join the waitlist”. Link to waitlist. | / |
| Create @kameapp TikTok | Mirror IG bio and branding. | Deprioritize |
| Set up Linktree | Free tier. Links: Waitlist, Instagram, TikTok. Add to all bios. | Deprioritize |
| Jo: Update personal IG bio | Add “Building @kameapp ¦ Ex-BCG” to name field. | Deprioritize |

### Day 2 (Tuesday) — Landing Page Build

Owner: Jo (4h)

| Task | Details | Done? |
| --- | --- | --- |
| Build landing page | Use Framer (free) or Carrd ($9/yr). Single page: hero headline + 3s video/GIF + email field + CTA. | ☐ |
| Embed GetWaitlist widget | Follow GetWaitlist embed docs. Test signup → confirmation → referral page flow. | ☐ |
| Connect domain | Point joinkame.com to Framer/Carrd. SSL auto-configured. | ☐ |
| Set up Google Analytics | Add GA4 tag to landing page. Set up conversion event for signups. | ☐ |
| Test full flow end-to-end | Signup → email confirmation → referral page → share buttons all work. | ☐ |

### Day 3 (Wednesday) — Design System & Content Templates

Owner: Ryan (3h) + Jo (2h)

| Task | Details | Done? |
| --- | --- | --- |
| Set up Canva Pro | $13/mo. Create Kame Brand Kit: colors (#112836, #48E6CD, #FA6869), fonts (Plus Jakarta Sans), logo. | ☐ |
| Create 5 IG post templates | Carousel template, Reel cover template, Story template, Quote card, Product showcase. All in Kame brand. | ☐ |
| Create AI try-on demo assets | Use 3 best FASHN API outputs. Format as before/after carousels and transition Reels. | ☐ |
| Write first 10 captions | Use Claude to draft. Mix of: 3 try-on demos, 3 founder BTS, 2 fashion tips, 2 waitlist CTAs. | ☐ |
| Create hashtag sets | Primary: #KameFashion #AITryOn #VirtualTryOn #FashionTech. Secondary: #OnlineShopping #OOTD #StyleTech. | ☐ |

### Day 4 (Thursday) — Automation Pipeline Setup

Owner: Jo (4h)

| Task | Details | Done? |
| --- | --- | --- |
| Set up Buffer (free tier) | Connect IG + TikTok. Free: 3 channels, 10 scheduled posts/channel. | ☐ |
| Set up n8n cloud | Sign up n8n.io cloud ($20/mo). Or self-host free on Railway. | ☐ |
| Create content queue | Google Sheets: columns for Date, Platform, Content Type, Caption, Media URL, Status, Performance. | ☐ |
| Build n8n workflow #1 | Google Sheets → AI caption enhancement (Claude API) → Buffer API → auto-schedule. See Section 9. | ☐ |
| Set up CapCut account | Free. Download mobile + desktop. Import Kame brand colors as presets. | ☐ |

### Day 5 (Friday) — Content Production Day #1

Owner: Jo (4h) + Ryan (2h)

| Task | Details | Done? |
| --- | --- | --- |
| Record 3 Reels | Reel 1: “What my BCG colleagues don’t know I’m building” (Jo BTS). Reel 2: AI try-on demo transition. Reel 3: Fashion fail → Kame fix. | ☐ |
| Edit in CapCut | Add captions (auto-caption feature), trending audio, text overlays. Export 1080x1920. | ☐ |
| Create 2 carousels | Carousel 1: “5 outfits under $50.” Carousel 2: “How online shopping fails you (and how AI fixes it).” | ☐ |
| Schedule first week | Load into Buffer. Schedule: Tue/Thu/Sat for brand, Mon/Wed/Fri for founder. | ☐ |
| Test cross-post to TikTok | Ensure Buffer auto-posts to TikTok. Remove IG watermark. Adjust captions for TikTok style. | ☐ |

### Days 6–7 (Weekend) — Soft Launch & Network Seeding

Owner: Both (2h each day)

| Task | Details | Done? |
| --- | --- | --- |
| Share waitlist to personal networks | WhatsApp groups, university alumni, BCG/JP Morgan colleagues, LinkedIn connections. | ☐ |
| Jo: Post LinkedIn announcement | “I’m building something. After 3 years at BCG, I’m solving the #1 frustration in online fashion...” with waitlist link. | ☐ |
| Ryan: Post LinkedIn announcement | Parallel post from foodpanda/strategy angle. | ☐ |
| Engage on 20 fashion IG accounts | Leave genuine comments on fashion content creators. No spam. Build visibility. | ☐ |
| Submit to BetaList | Free listing. Write compelling 2-line pitch for BetaList.com. | ☐ |
| Target by end of Day 7 | 100–200 waitlist signups from warm network alone. | ☐ |

## WEEK 2: Content Cadence & Influencer Seeding

### Day 8 (Monday) — Influencer Outreach Begins

Owner: Ryan (3h)

| Task | Details | Done? |
| --- | --- | --- |
| Build target list | Find 50 nano-influencers (1K–10K followers) in fashion/style niche on IG. Use IG search + hashtag browsing. | ☐ |
| Write DM template | “Hey [name]! Building an AI app that shows you how clothes look ON YOU before buying. We’re giving early beta access to fashion creators. Interested?” | ☐ |
| Send first 20 DMs | Personalize each one. Reference their recent post. Don’t copy-paste. | ☐ |
| Set up tracking sheet | Google Sheet: Name, Handle, Followers, DM Sent Date, Response, Status, Content Posted. | ☐ |

### Day 9 (Tuesday) — Content Production Day #2

Owner: Jo (4h)

| Task | Details | Done? |
| --- | --- | --- |
| Record 3 more Reels | Reel 4: Vibe coding session (screen recording + face cam). Reel 5: “Day 1 vs Day 30 of building Kame.” Reel 6: UI walkthrough teaser. | ☐ |
| Edit and schedule | CapCut editing. Schedule for remainder of Week 2. | ☐ |
| Create 3 Stories | Poll: “Biggest online shopping frustration?”. BTS: desk setup. Waitlist counter update. | ☐ |
| Respond to all comments/DMs | First hour after each post goes live. Engage every comment with 5+ word response. | ☐ |

### Days 10–11 (Wed–Thu) — Community & Outreach

Owner: Ryan (2h/day)

| Task | Details | Done? |
| --- | --- | --- |
| Send 30 more influencer DMs | Second batch. Aim for 10–15 total responses from 50 outreaches. | ☐ |
| Submit to Product Hunt Upcoming | Create PH profile. Submit Kame to Upcoming Products section. | ☐ |
| Post in Reddit communities | r/startups, r/fashiontech, r/Entrepreneur. Genuine value posts, not spam. Share the founder story. | ☐ |
| Create IG Broadcast Channel | Name: “Kame Insiders.” Invite waitlist signups who follow. Post exclusive BTS updates. | ☐ |
| Follow-up with influencer responders | Send product demo (AI try-on screenshot). Agree on content deliverable. | ☐ |

### Day 12 (Friday) — Content Batch #3 & Performance Review

Owner: Jo (3h) + Ryan (1h)

| Task | Details | Done? |
| --- | --- | --- |
| Batch produce Week 3 content | Record 4 Reels, create 2 carousels. Focus on what performed best in Week 1–2. | ☐ |
| Review analytics | Check: Which Reels had highest watch time? Which drove most waitlist clicks? Which got DM shares? | ☐ |
| Double down on winners | If BTS Reels outperform try-on demos (or vice versa), shift ratio toward what works. | ☐ |
| Update content queue sheet | Mark performance data. Plan Week 3–4 content based on learnings. | ☐ |

### Days 13–14 (Weekend) — Automation Refinement & Waitlist Push

Owner: Both (2h each)

| Task | Details | Done? |
| --- | --- | --- |
| Refine n8n workflows | Fix any issues from Week 1. Add: auto-DM thank you to new followers. Auto-repost top content to TikTok. | ☐ |
| First waitlist milestone post | “We just hit [X] signups! Here’s what we’re building for you...” Celebrate with community. | ☐ |
| Send first email update to waitlist | Behind-the-scenes: what we built this week, sneak peek of a feature, “refer a friend” reminder. | ☐ |
| Plan Week 3–4 influencer content | Coordinate with 5–10 nano-influencers who responded. Set content dates. | ☐ |
| End of Sprint Target | 500+ waitlist signups. 15+ pieces of content published. 5+ influencer partnerships initiated. | ☐ |

# 9. Automated Marketing Workflow: The Kame Marketing OS

Goal: Build a centralized, AI-powered marketing system that automates repetitive tasks while keeping human creative control over strategy and brand voice. This section covers tool selection, agentic workflow architecture, and step-by-step setup.

## 9.1 Marketing Function Tool Comparison

### A. Content Scheduling & Publishing

| Tool | Price | Pros | Cons | Verdict |
| --- | --- | --- | --- | --- |
| Buffer | Free (3ch, 10 posts) → $5/ch/mo | Simple, reliable, free tier good for start. IG + TikTok + LinkedIn. | Limited analytics on free tier. No AI caption gen. | ✅ START HERE |
| Later | $16.67/mo | Visual planner, drag-and-drop calendar. Best for IG-first brands. Link-in-bio tool. | Pricier than Buffer. 30 posts/profile on starter. | Upgrade to later |
| SocialBee | $29/mo | AI copilot generates full strategy. Category-based scheduling. Content recycling. | Steeper learning curve. Overkill for 2-person team initially. | Consider at 5K followers |
| Publer | $5–$12/mo | Cheapest paid option. AI assist included. Bulk scheduling. | Less polished UI. Fewer templates. | Good budget option |

Recommendation: Start with Buffer free tier. Move to Later or SocialBee when you hit 3+ accounts and 5K followers.

### B. Content Creation & Editing

| Tool | Price | Pros | Cons | Verdict |
| --- | --- | --- | --- | --- |
| Canva Pro | $13/mo | Brand kit, templates, Magic Write AI, video editing, direct IG publish. | Video editing limited vs CapCut. Carousel export needs manual tweaking. | ✅ ESSENTIAL |
| CapCut | Free | Best free video editor. Auto-captions, trending templates, effects. TikTok-native. | Desktop version less powerful than mobile. Some pro effects paywalled. | ✅ ESSENTIAL |
| Opus Clip | $15/mo | Auto-clips long videos into viral shorts. AI picks best moments. | Needs source video first. Not for from-scratch creation. | Use when you have long-form |
| Predis.ai | $29/mo | Full post generation from text prompt (image + caption). Multi-platform. | Generic feel if not customized. Quality varies. | Optional add-on |

Recommendation: Canva Pro + CapCut (free) covers 95% of content creation needs. Add Opus Clip when you start making longer Reels.

### C. AI Caption & Strategy Generation

| Tool | Price | Pros | Cons | Verdict |
| --- | --- | --- | --- | --- |
| Claude (Anthropic) | Already using | Best long-form strategy, brand voice training, caption batching. Can generate 20 captions in one prompt. | Not integrated into scheduling tools natively. | ✅ PRIMARY AI |
| ChatGPT | Free / $20/mo | Good for quick caption variations. Image generation (DALL-E). | Less consistent brand voice than Claude for long batches. | Secondary / image gen |
| Flick Iris | $14/mo | IG-specific AI. Learns your business, suggests strategy, generates captions + hashtags. | IG-only. Less flexible than Claude. | Optional IG specialist |

Recommendation: Claude as primary AI brain (already in your stack). ChatGPT for image generation. Flick optional for hashtag research.

### D. Workflow Automation (The Agentic Layer)

| Tool | Price | Pros | Cons | Verdict |
| --- | --- | --- | --- | --- |
| n8n | Free (self-host) or $20/mo cloud | Open-source. Self-hostable on Railway. Native IG node via Meta Graph API. No per-task fees. Most flexible. | Requires setup time. Technical learning curve. | ✅ RECOMMENDED |
| Make.com | Free (100 ops) → $9/mo | Visual builder. 7+ IG templates. Easier learning curve than n8n. Already connected to your Claude project. | Per-operation pricing adds up. Less control than n8n. | Good alternative |
| Zapier | $19.99/mo | Easiest setup. Largest app directory. | Most expensive per-task. Limited free tier. Less customizable. | Not recommended (cost) |

Recommendation: n8n self-hosted on Railway (free, since you already use Railway) or Make.com if you prefer visual builder. n8n gives most control and zero marginal cost.

### E. Waitlist & Email

| Tool | Price | Pros | Cons | Verdict |
| --- | --- | --- | --- | --- |
| GetWaitlist | $15/mo | Best referral waitlist. Embeddable widget. Built-in email sequences. Analytics dashboard. | Limited design customization. | ✅ RECOMMENDED |
| KickoffLabs | $29/mo | More gamification options. Robinhood-style template. A/B testing. | Pricier. More than needed for MVP. | If you want more gamification |
| Mailchimp | Free (500 contacts) | Best free email tool for nurture sequences beyond what GetWaitlist offers. | Separate from waitlist. Manual sync needed. | Add for advanced email |

### F. Analytics & Performance Tracking

| Tool | Price | Pros | Cons | Verdict |
| --- | --- | --- | --- | --- |
| Instagram Insights | Free | Native. Most accurate data. Reach, impressions, shares, saves, profile visits. | No cross-platform view. No export to sheets natively. | ✅ PRIMARY |
| Metricool | Free tier | Cross-platform analytics. Organic + paid in one view. Competitor benchmarking. | Free tier limited. $22/mo for full features. | Add when scaling |
| Google Sheets dashboard | Free | Custom dashboard pulling from GetWaitlist API + IG Insights manual entry. Full control. | Manual data entry until n8n automates it. | ✅ START HERE |

## 9.2 The Kame Marketing OS: Total Monthly Cost

| Tool | Tier | Monthly Cost |
| --- | --- | --- |
| Buffer | Free (upgrade to $5/ch later) | $0 |
| Canva Pro | Pro | $13 |
| CapCut | Free | $0 |
| GetWaitlist | Starter | $15 |
| n8n | Self-hosted on Railway (or $20 cloud) | $0–$20 |
| Claude | Already in use | $0 |
| Google Sheets | Free | $0 |
| Framer / Carrd | Landing page | $0–$10 |
| Domain | Annual | ~$1/mo |
| TOTAL |  | $29–$59/month |

## 9.3 Agentic Workflow Architecture: What Gets Automated

The following diagram shows what is automated vs. human-controlled. Rule: Automate distribution, keep creative human.

| Function | Automated? | How | Human Input Needed |
| --- | --- | --- | --- |
| Caption generation | ⚠️ Semi | Claude API drafts 20 captions/week from content pillars. n8n triggers weekly. | Review, tweak brand voice, approve |
| Hashtag research | ✅ Yes | Flick or manual set. Store 5 hashtag sets in Google Sheets. Auto-attach per content type. | Update sets monthly |
| Post scheduling | ✅ Yes | Buffer auto-publishes from content queue at optimal times. | Load content + set dates |
| Cross-platform posting | ✅ Yes | n8n: IG post → auto-reformat for TikTok + Threads. One upload, 3 platforms. | None after setup |
| Video editing | ❌ No | CapCut manual editing. Auto-captions are automated, but creative cuts are human. | Full creative control |
| Reel recording | ❌ No | Must be filmed by Jo/Ryan. Authenticity is the whole point. | This IS the product |
| Carousel design | ⚠️ Semi | Canva templates with brand kit. Drag in new content. AI suggests layouts. | Choose images, write copy |
| Email to waitlist | ✅ Yes | GetWaitlist auto-sends confirmation + referral link. Bi-weekly updates via Mailchimp drip. | Write update content bi-weekly |
| Influencer outreach | ⚠️ Semi | n8n: pull from target list sheet → generate personalized DM via Claude → draft in Google Doc. | Manually send DMs (IG limits automation) |
| Performance tracking | ✅ Yes | n8n: pull IG Insights + GetWaitlist data daily → push to Google Sheets dashboard. | Weekly review + strategy adjustment |
| Comment replies | ⚠️ Semi | n8n flags new comments. Claude suggests replies. Human approves/sends. | Approve replies in first hour post-publish |
| Trend monitoring | ✅ Yes | n8n: daily scrape of #AIFashion #VirtualTryOn hashtags → alert via Telegram/Slack. | Decide whether to create response content |

## 9.4 Step-by-Step: Setting Up the n8n Agentic Workflow

### Workflow 1: Weekly Content Generation Pipeline

Trigger: Every Sunday 9am (cron). Flow: Google Sheets (content pillars) → Claude API (generate 10 captions) → Google Sheets (write to content queue) → Slack/Telegram notification (“10 new captions ready for review”).

Setup time: 2 hours. Saves: 3+ hours/week of caption writing.

### Workflow 2: Auto-Post from Content Queue

Trigger: Scheduled times from content queue. Flow: Google Sheets (get next scheduled post) → Check status = “Approved” → Meta Graph API (publish to IG) → Update sheet status to “Published” → Auto-reformat caption for TikTok → TikTok API (publish).

Setup time: 3 hours. Saves: 30 min/day of manual posting.

### Workflow 3: Daily Performance Dashboard

Trigger: Daily 8am. Flow: Instagram Graph API (pull yesterday’s metrics: reach, shares, saves, profile visits) → GetWaitlist API (pull signups, referral rate) → Google Sheets (append to dashboard tab) → Telegram notification with daily summary.

Setup time: 2 hours. Saves: 20 min/day of manual analytics checking.

### Workflow 4: Influencer Outreach Assistant

Trigger: Manual (when adding new targets to sheet). Flow: Google Sheets (new row in influencer list) → Claude API (generate personalized DM based on their recent posts, follower count, and niche) → Google Doc (draft DM for human review) → Telegram notification (“5 new DM drafts ready”).

Setup time: 1.5 hours. Saves: 1+ hour/batch of outreach.

### Workflow 5: Trend Alert Monitor

Trigger: Every 6 hours. Flow: Web scrape / API call for #AIFashion #VirtualTryOn #OnlineShoppingFail trending posts → Filter for posts with 1000+ engagement → Claude API (summarize trend + suggest response content) → Telegram alert with suggestion.

Setup time: 2 hours. Ensures you never miss a trending moment relevant to Kame.

### Meta API Setup (Required for n8n IG Automation)

Important: Instagram publishing automation requires a Meta Developer App with Instagram Graph API access. Steps:

- Create Meta Developer account at developers.facebook.com

- Create a new App (type: Business). Add Instagram Graph API product.

- Connect your Instagram Business account to a Facebook Page (required by Meta).

- Generate a long-lived access token (valid 60 days, auto-refreshable via n8n).

- Approval timeline: Instant for basic permissions. 7–30 days for advanced (publishing). Start this on Day 1.

- Note: Only publishing automation is allowed by Meta. Engagement automation (auto-likes, auto-follows) will get you banned.

# 10. Risks & Mitigations

Low initial traction: Seed waitlist through personal networks first (200–300 warm contacts). Use LinkedIn for professional network. Submit to BetaList, Product Hunt, Reddit.

Content burnout: Batch weekly (one production day). Use templates. Repurpose: one Reel → TikTok + Story + carousel + LinkedIn post. AI caption generation saves 3+ hours/week.

Try-on demos look unimpressive: Cherry-pick best FASHN outputs. Only show results that look genuinely good. Quality over quantity.

Waitlist fatigue: Send bi-weekly email updates. Use milestone celebrations. Never go 2+ weeks without communication.

Meta API approval delay: Apply on Day 1. Use Buffer as backup scheduler until API is approved (Buffer uses their own approved API).

Algorithm changes: Diversify across IG + TikTok + LinkedIn. Never depend on one platform. Broadcast Channel builds owned audience.

Kame — See It, Swipe It, Own It

Marketing Strategy V2.0 — March 2026 — Confidential

Gmail KAME Mail pse: bnpohjtarmxoggwu